## Sheet1
ID	Module	Name	Description	Difficulty	Owner	Status	Completion Date
1	UI	print_table			Bendi
2	UI	print_result			Bálint
3	UI	print_menu			done by default	done	01/14/19
4	UI	get_inputs			Marci
5	UI	print_error_message			Laci
6	common	generate_random
7	data_manager	get_table_from_file
8	data_manager	write_table_to_file
9	accounting	start_module			Laci
10	accounting	show_table			Laci
11	accounting	add			Laci
12	accounting	remove			Laci
13	accounting	update			Laci
14	accounting	which_year_max			Laci
15	accounting	avg_amount			Laci
16	crm	start_module			Bálint
17	crm	show_table			Bálint
18	crm	add			Bálint
19	crm	remove			Bálint
20	crm	update			Bálint
21	crm	get_longest_name_id		2	Bálint	done	10/14/19
22	crm	get_subscribed_emails		3	Bálint	done	10/14/19
23	hr	start_module			Marci
24	hr	show_table			Marci
25	hr	add			Marci
26	hr	remove			Marci
27	hr	update			Marci
28	hr	get_oldest_person			Marci
29	hr	get_person_closest_to_average			Marci
30	inventory	start_module			Bendi
31	inventory	show_table			Bendi
32	inventory	add			Bendi
33	inventory	remove			Bendi
34	inventory	update			Bendi
35	inventory	get_available_items			Bendi
36	inventory	get_average_durability_by_manufacturer			Bendi
37	sales	start_module
38	sales	show_table
39	sales	add
40	sales	remove
41	sales	update
42	sales	get_lower_price_item_id
43	sales	get_items_sold_between
44	store	start_module
45	store	show_table
46	store	add
47	store	remove
48	store	update
49	store	get_counts_by_manufacturers
50	store	get_average_by_manufacturer